## Project Planner
ACTIVITY | PLAN START | PLAN DURATION | PERIODS
|  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
Inception Phase | 1 | 1 | bar: PERIODS 1
Development of public procurement Open Data OCDS for pilot country jurisdiction | 2 | 2
Prepare a localized OCDS public procurement data set for a smart public contract register | 3 | 1
Implementation of the Open Contracting Data Standard | 4 | 3
Implementing the OCDS analytical tools | 6 | 2
Design and develop a public access portal for the OCDS contract register | 7 | 2
Assist with implementing the OCDS red flags monitoring tool | 8 | 2
Facilitate stakeholder engagement | 9 | 4
Evaluation phase | 13 | 1
Closing Phase | 14 | 1